## Project Schedule
Create a Project Schedule in this worksheet. Enter title of this project in cell B1. Information about how to use this worksheet, including instructions for screen readers and the author of this workbook is in the About worksheet. Continue navigating down column A to hear further instructions. | Energy Mobile | [5 empty] | SIMPLE GANTT CHART by Vertex42.com
Enter Company Name in cell B2. | MGIS 2021 | [5 empty] | https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html
Enter the name of the Project Lead in cell B3. Enter the Project Start date in cell E3. Pooject Start: label is in cell C3. | Cole Anderson | Project Start: |  | 2021-09-09
The Display Week in cell E4 represents the starting week to display in the project schedule in cell I4. The project start date is considered Week 1. To change the display week, simply enter a new week number in cell E4. The starting date for each week, starting with the display week from cell E4, starts in cell I4 and is auto calculated. There are 8 weeks represented in this view from cell I4 through cell BF4. You should not modify these cells. Display Week: label is in cell C4. |  | Display Week: |  | 1 |  |  | 2021-09-06 | [6 empty] | 2021-09-13 | [6 empty] | 2021-09-20 | [6 empty] | 2021-09-27 | [6 empty] | 2021-10-04 | [6 empty] | 2021-10-11 | [6 empty] | 2021-10-18 | [6 empty] | 2021-10-25 | [6 empty] | 2021-11-01 | [6 empty] | 2021-11-08 | [6 empty] | 2021-11-15 | [6 empty] | 2021-11-22 | [6 empty] | 2021-11-29 | [6 empty] | 2021-12-06 | [6 empty] | 2021-12-13
Cells I5 through BL5 contain the day number for the week represented in the cell block above each date cell and are auto calculated. You should not modify these cells. Today's date is outlined in Red (hex #AD3815) from today's date in row 5 through the entire date column to the end of the project schedule. | time axis 2021-09-06 to 2021-12-19
This row contains headers for the project schedule that follows below them. Navigate from B6 through BL 6 to hear the content. The first letter of each day of the week for the date above that heading, starts in cell I6 and continues through cell BL6. All project timeline charting is auto generated based on the start and end dates entered, using conditional formats. Do not modify content in cells within columns after column I starting with cell I7. | TASK | MILESTONE | PROGRESS | START | END | DAYS | time axis 2021-09-06 to 2021-12-19
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the curren day within the project schedule.
Cell B8 contains the Phase 1 sample title. Enter a new Title in cell B8. Enter a name to assign the phase to, if it applies for your project, in cell C8. Enter Progress for the entire phase, if it applies for your project, in cell D8. Enter the start and end dates for the entire phase, if it applies for your project, in cells E8 and F8. The Gantt chart will automatically fill in the appropriate dates and shade according to the progress entered. To delete the phase and work only from tasks, simply delete this row. | Research/Speculation | All research and methods found, outline complete | 100% | 2021-09-09 | 2021-09-16 | 8
Cell B9 contains the sample task "Task 1." Enter a new task name in cell B9. Enter a person to assign the task to in cell C9. Enter progres of the task in cell D9. A progress bar appears in the cell and is shaded according to the number in the cell. For example, 50 percent progress would shade half of the cell. Enter task start date in cell E9. Enter task end date in cell F9. A status bar shaded for the dates entered appears in blocks starting from cell I9 through BL9. | Find 4-5 papers to reference | Find: methods of slope, affects on various needs | 100% | 2021-09-09 | 2021-09-23 | 15
Cell B9 contains the sample task "Task 1." Enter a new task name in cell B9. Enter a person to assign the task to in cell C9. Enter progres of the task in cell D9. A progress bar appears in the cell and is shaded according to the number in the cell. For example, 50 percent progress would shade half of the cell. Enter task start date in cell E9. Enter task end date in cell F9. A status bar shaded for the dates entered appears in blocks starting from cell I9 through BL9. | Finalize chart | Present final chart | 100% | 2021-09-09 | 2021-09-16 | 8
Rows 10 through 13 repeat the pattern from row 9. Repeat the instructions from cell A9 for all task rows in this worksheet. Overwrite any sample data. A sample of another phase starts in cell A14. Continue entering tasks in cells A10 through A13 or go to cell A14 to learn more. | Read over previous model paper/code for foundation |  | 100% | 2021-09-09 | 2021-09-16 | 8
The cell at right contains the Phase 2 sample title. You can create a new phase at any time within column B. This project schedule does not require phases. To remove the phase, simply delete the row. To create a new phase block in this row, enter a new Title in cell at right. To continue adding tasks to the phase above, enter a new row above this one and fill in the task data as in cell A9's instruction. Update the Phase details in cell at right based on cell A8's instruction. Continue navigating down column A cells to learn more. If you haven't added any new rows in this worksheet, you will find 2 additional sample phase blocks have been created for you in cells B20 and B26. Otherwise, navigate through column A cells to find the additional blocks. Repeat the instructions from cells A8 and A9 whenever you need to. | Planning/Outline | Establish a firm plan for project | 100% | 2021-09-09 | 2021-09-23 | 15
| Arvix submission digging | Account and required outline | 100% | 2021-09-09 | 2021-09-16 | 8
| Outline repo, presentation, paper | Register account, know guidelines | 100% | 2021-09-12 | 2021-09-16 | 5
| Plot spatial data workflow | Sensical workflow diagram | 100% | 2021-09-14 | 2021-09-15 | 2
| Feedback on workflow | Revised workflow; in class | 100% | 2021-09-15 | 2021-09-16 | 2
Sample phase title block | Data | Data evaluated, data processing cleaned | 100% | 2021-09-23 | 2021-09-30 | 8
| Quality evaluation of current data | Roadways and elevation evaluated for accuracy/granularity | 100% | 2021-09-23 | 2021-09-24 | 2
| Gather new data if needed | All data gathered | 100% | 2021-09-24 | 2021-09-25 | 2
| Clean up ETL (only)for hard-coding | ETL is minimal and convenient | 100% | 2021-09-23 | 2021-09-26 | 4
| Find API to translate clicks to points | Method understood and signed up for if needed | 100% | 2021-09-23 | 2021-09-30 | 8
Sample phase title block | Analysis | Base of all calculations created | 100% | 2021-09-30 | 2021-11-12 | 44
| Create formulas for slope | Formula that fixes "average slope" problem | 100% | 2021-09-30 | 2021-10-05 | 6
| Create formulas for slope | Formula that fixes "zero" problem | 100% | 2021-09-30 | 2021-10-05 | 6
| Create formulas for transit modes | 3 transit modes where slope/distance have different effects | 100% | 2021-10-05 | 2021-10-10 | 6
| Create restictions for transit modes | Restrictions do not allow to cross dangerous roads, steep roads | 100% | 2021-10-10 | 2021-10-14 | 5
| Point-click conceptualized | Interface where click is translated to coordinate | 100% | 2021-10-14 | 2021-10-18 | 5
| Build network and router | Functioning route planner | 100% | 2021-10-18 | 2021-10-24 | 7
| Get all processes working in code | Functioning code prototype | 100% | 2021-10-24 | 2021-11-12 | 20
Cell B8 contains the Phase 1 sample title. Enter a new Title in cell B8. Enter a name to assign the phase to, if it applies for your project, in cell C8. Enter Progress for the entire phase, if it applies for your project, in cell D8. Enter the start and end dates for the entire phase, if it applies for your project, in cells E8 and F8. The Gantt chart will automatically fill in the appropriate dates and shade according to the progress entered. To delete the phase and work only from tasks, simply delete this row. | Draft 1 | Revise deliverables (testing) | 100% | 2021-11-12 | 2021-11-18 | 7
Rows 10 through 13 repeat the pattern from row 9. Repeat the instructions from cell A9 for all task rows in this worksheet. Overwrite any sample data. A sample of another phase starts in cell A14. Continue entering tasks in cells A10 through A13 or go to cell A14 to learn more. | Draft: Test code blocks for accuracy of model and scripting errors | Error tested code with comments | 100% | 2021-11-12 | 2021-11-16 | 5
| Draft paper with notes | paper deliverable draft | 100% | 2021-11-12 | 2021-11-16 | 5
| Gather and provide feedback | In class | 100% | 2021-11-17 | 2021-11-18 | 2
Cell B8 contains the Phase 1 sample title. Enter a new Title in cell B8. Enter a name to assign the phase to, if it applies for your project, in cell C8. Enter Progress for the entire phase, if it applies for your project, in cell D8. Enter the start and end dates for the entire phase, if it applies for your project, in cells E8 and F8. The Gantt chart will automatically fill in the appropriate dates and shade according to the progress entered. To delete the phase and work only from tasks, simply delete this row. | Communicating Results/Final | Submit final deliverables | 80% | 2021-11-18 | 2021-12-16 | 29
| Revise script based on feedback/prev. issues | Final code script with comments completed and cleaned | 100% | 2021-11-18 | 2021-12-17
Cell B9 contains the sample task "Task 1." Enter a new task name in cell B9. Enter a person to assign the task to in cell C9. Enter progres of the task in cell D9. A progress bar appears in the cell and is shaded according to the number in the cell. For example, 50 percent progress would shade half of the cell. Enter task start date in cell E9. Enter task end date in cell F9. A status bar shaded for the dates entered appears in blocks starting from cell I9 through BL9. | Revise paper based on feedback | Paper deliverable complete | 75% | 2021-11-18 | 2021-12-17 | 30
| Finalize Repo | Clean Repo | 75% | 2021-12-19 | 2021-12-20 | 2
| Submit paper to Arvix using guidelines | Final paper submitted | 100% | 2021-12-20 | 2021-12-22 | 3

## Slope Calc
Equations Testing Matrix
Scaling on either of these?
2.) Slope Re-map Equation
|  | SRE1 | SRE2 | SRE3 | SRE4
1.) Slope Calc. Equation | SC1 | 1.) (Zstart - Zend)/Length | 1.) (Zstart - Zend)/Length | 1.) (Zstart - Zend)/Length | 1.) (Zstart - Zend)/Length
### These Z's are not options? |  | 2.) Leave values, all segments with slope 0 will have energy zero | 2.) all zeros become next smallest value | 2.) remap all from 1-100 | 2.) remap all from 1-10
| SC2 | 1.) @ Elevation step | 1.) @ Elevation step | 1.) @ Elevation step | 1.) @ Elevation step
|  | 2.) Leave values, all segments with slope 0 will have energy zero | 2.) all zeros become next smallest value | 2.) remap all from 1-100 | 2.) remap all from 1-10
| SC3 | 1.) (Zmax- Zmin)/Length | 1.) (Zmax- Zmin)/Length | 1.) (Zmax- Zmin)/Length | 1.) (Zmax- Zmin)/Length
|  | 2.) Leave values, all segments with slope 0 will have energy zero | 2.) all zeros become next smallest value | 2.) remap all from 1-100 | 2.) remap all from 1-10
How do I get Variables in a travel mode? Create and then modify in customization or can be created in Arc?
it really messes up on bridges because it assumes the road follows the bank's slope

## Remap
new_sml + (x-old_sml)(new_lg-new_sml)/(old_lg-old_sml)
[0,40] |  | [1,10] | 1+(x-0)(10-1)/(40-0) | 1+10x/40 | 1+X/4 | 1+.25x
[0,40] |  | [1,100] | 1+(x-0)(100-1)/(40-0) | 1+ 100x/40 | 1+ 5x/2 | 1+2.5x
Energy Equations
(distance)(slope)(breakdown)(1-breakdown)
(distance)(distance factor) + (slope)(slope factor)

## Route Testing
1:01
Seg | Dist | Slope
634 | 14.9 | 14.12 | [5 empty] | 634 | 14.89 | 14.12
844 | 7.6 | 30.22 | [5 empty] | 555 | 1.29 | 5.9
421 | 10.2 | 14.9 | [5 empty] | 719 | 4.3 | 2.74
857 | 10.9 | 19.5 | [5 empty] | 453 | 42.6 | 8.8
797 | 9.16 | 1.7 | [5 empty] | 706 | 3.53 | 8.45
231 | 2.1 | 1.4 | [6 empty] | 66.61 | 40.01
40 | 7.63 | 1.37 | [5 empty] | FACTOR | *2 | *1 | 173.21
802 | 10.7 | 0.6 | 42 | 1.7 | 3.02 | 24.48 | 4.72
141 | 1.23 | 0.5
529 | 10.7 | 0.75
309 | 2.75 | 7.6
711 | 7.8 | 3.1
207 | 16.8 | 2.44
796 | 7.8 | 2.8 | [7 empty] | Test2
64 | 2.4 | 2.1
140 | 16.5 | 1.56 | 10 | 3.71 | 1.244 | 34.46 | 4.954 |  |  | 2*[Dist_Cust]+1*[Slope_Cust] | same route | 2*[Dist_Cust]+[Slope_Cust]
402 | 14.7 | 1.7
534 | 1.56 | 2.55 | 23 | 2.59 | 0.5 | 63.66 | 4.99 |  | Route1 | 1*[Dist_Cust]+1*[Slope_Cust] | NOT same | [Dist_Cust]+[Slope_Cust]
363 | 3.1 | 3.2 | 527 | 1.4 | 0.5 |  |  |  | Route2 | 1*[Dist_Cust]+1*[Slope_Cust] | NOT same | [Dist_Cust]+[Slope_Cust]
672 | 1.84 | 1.27
233 | 6.86 | 1.3
704 | 7.6 | 2.65 | [6 empty] | MUST BE "1*[Dist_Cust]+1*[Slope_Cust]"
661 | 6.86 | 0.65
401 | 7.46 | 0.7
823 | 5 | 0.8
830 | 8.86 | 1.4
792 | 17.7 | 0.63
180 | 20.85 | 1.8
22 | 14.44 | 1
775 | 2.3 | 3.6
508 | 21.9 | 2.2
593 | 9.37 | 22
310 | 2.09 | 38.9
608 | 6 | 17
532 | 5.4 | 13.4
409 | 4.78 | 50
413 | 8.2 | 12.5
432 | 10.35 | 9.6
859 | 14.7 | 9.4
| 341.09 | 302.91 | 644

## Route Table
D/S
R1
730 S 8th St, Minneapolis, MN, 55415 |  |  |  | 40:1 | 10:1 | 4:1 | 2:1 | 1:1 | 1:4 | 1:6 | 1:7 | 1:8 | 1:9 | 1:10 | 1:11 | 1:12 | 1:13 | 1:14 | 1:15 | 1:20 | 1:30 | 1:40
to | 1:6:1:7 | + w/o test | R1_ |  | R1_101 | R1_41 |  | R1_11 | R1_14 |  |  |  |  | R1_110
701 24th Ave SE, Minneapolis, MN, 55414 |  |  | R2_ |  | R2_101 | R2_41 |  | R2_11 | R2_14 |  |  |  |  | R2_110
|  |  | R3_ |  | R3_101 | R3_41 |  | R3_11 | R3_14 |  |  |  |  | R3_110
R2 |  |  | R4_ |  | R4_101 | R4_41 |  | R4_11 | R4_14 |  |  |  |  | R4_110
1199 Yale Ave SE, Minneapolis, MN, 55414 |  |  | R5_
to
414 SE 7th Ave, Minneapolis, MN, 55414
|  |  |  | 40/1 | [8 empty] | 1/9 |  | 1/11 | [6 empty] | 1/40
R3
2107 21st Ave S, Minneapolis, MN, 55404 |  | 1:10- 1:11
to
1625 4th St SE, Minneapolis, MN, 55455
R4
800 University Ave SE, Minneapolis, MN, 55414
to
101 19th Ave S, Minneapolis, MN, 55454
R5
212 3rd Ave S, Minneapolis, MN 55401
to
301 St Anthony Ave, Minneapolis, MN 55414